## Slide 1
24-94. Presentation, update, and discussion on the Coll Street Drainage project – Phase 1
  Scott McClelland, Assistant Director of Transportation and Capital Improvements
  Nolan Pierce, P.E.
    Kimley-Horn

## Slide 2
Project Update for
Coll Street Improvements
From Castell Ave to Comal River
Castell Avenue Phase I
January 24, 2024

## Slide 3: Overview
Project Background/History
Progress to Date
Proposed Improvements
Enhanced Additives
Cost
Schedule
Questions
Project Limits

## Slide 4: Project Background/History
Project Objective – combine efforts for future infrastructure needs identified in the PER for Castell Avenue and the Downtown ROW Enhancements preliminary study
Downstream drainage infrastructure capacity increases needed for Castell Avenue (increase size of storm system to Comal River)
Pedestrian walkability and enhancements identified along Coll Street
Existing 100-year storm flooding
Notes: Keep or delete this slide?

## Slide 5
Progress to Date
Data Collection – 100% Complete
  Survey
  Geotechnical & Pavement Design
  Environmental Study
Construction Drawings – 60% Complete
  Plans
  Enhanced Improvement Alternatives Identified
  Construction Cost Estimate
Public Involvement
  Stakeholder Meeting with Property Owners – 1/9/2024

## Slide 6: Stakeholder Meeting
Conducted on 1/9/2024 at Johnson Furniture
Received written and verbal comments
  Owners looking for enhanced communication and limit impacts as much as possible during construction and to limit impacts

## Slide 7
Proposed Improvements
Roadway Reconstruction
  New curbs, bulb-outs, and asphalt pavement
Internal Storm Drain System
Concrete Sidewalk (both sides)
Ped signal modifications at Seguin Ave
Water & Sewer Utility Replacements (Joint Bid w/NBU)

## Slide 8
Proposed Improvements – Overall Layout

## Slide 9
Enhanced Additives
Add Alternate 1
  Proposed Trees Only
Add Alternate 2
  Enhanced Landscaping including plantings and hardscape (no irrigation)
Add Alternate 3
  Underground Electric & Telecommunication conversion

## Slide 10: Add Alternates 1 & 2

## Slide 11: Add Alternate 3
Proposed Shared Duct Bank
Construction of Underground Duct Bank
  Limits include from Castell Ave to Comal Ave
  Requires utility coordination with multiple entities including NBU Electric, AT&T, etc.
4’ wide with multiple layers of conduit
Overground pedestals, ground boxes, and new service connections to property owners
Includes street lighting

## Slide 12: Underground Conversion Eye Level Image Examples
Before
After

## Slide 13: Underground Conversion Eye Level Image Examples
Before
After

## Slide 14: Underground Conversion Eye Level Image Examples
Before
After

## Slide 15
Opinion of Probable Construction Cost |  |  | 
Component | Subtotal | Contingency | Total
Base Construction - Roadway, Drainage, Ped Improvements | $5,145,000 | $775,000 | $5,920,000
Add Alternate 1 – Trees Only | $41,000 | $9,000 | $50,000
Add Alternate 2 – Enhanced Landscaping & Hardscape | $156,000 | $34,000 | $190,000
Add Alternate 3 – Underground Utility Conversion | $820,000 | $165,000 | $985,000
Totals | $6,162,000 | $983,000 | $7,145,000
Cost

## Slide 16: Schedule
Anticipated Project Schedule - Base | 
Includes: Roadway, Drainage, & W/WW | 
Task | Completion Date
Final Design | Summer 2024
Advertisement/Bidding | Fall 2024
Construction Start (18 Months*) | Begin 2025
Construction Complete | Summer 2026
Anticipated Project Schedule – Add Alternate 3 | 
Includes: Base + Added Underground Conversion | 
Task | Completion Date
Final Design | Summer 2024
Utility Coordination/Design (18 Months) | End 2025
Advertisement/Bidding | Spring 2026
Construction Start (18 Months*) | Summer 2026
Construction Complete | End 2027

## Slide 17: Questions?